Curriculum Review Plan

| Number/Aspect | Time | Goal(s) | Actions | Expected Outcomes | Delegation (including who involved) | Reporting | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BoT Requirements Starting Point: Vision | By end of 20XX | Have all starting points organised | SS & BOT to discuss what is required | To formulate a plan | BOT SS | Draw up Review Plan | Completed end 2008 |
| Geraldine Primary Vision (Mission Statement) What does this mean for children? What does this mean for teachers? | T4 20XX | (1) Review present Mission Statement (2) Whats good? What do we want to do more of? (3) Do less of? (4) Like us to do? | Parent Consultation Evening Newsletter opportunity for others Returns by 24 October | Data gathering around what parents think we do well, needs changed and more/less of | Bot & P | Feedback Parent Evening, August results to BOT, Staff, Community | Newsletter questions not well structured. |
| 2. Community Consultation & Involvement | 20XX | Parent Involvement Other Education providers, High School Kindy, Pre-School | Evening – Prizes Newsletter Invited to participate - | More parents contributing | Robbie – Evening LR Arrange | BOT informed & discuss Keep BOT informed – P | Positive |
| 3. Principles & Values |  | Decide on what we believe | Time to discuss and decide | Know what GPS's are |  |  |  |
| 4. NZ Curriculum Staff: pedagogy (teaching & learning) |  | To review GPS Philosophy & Pedagogy | Read New Curriculum Staff Meeting focusing on 7 areas P34 &35 | Staff will have Reviewed and discussed P | SS, | Staff Meeting 19/9/08 | More work required |
| 5. Core Curriculum Literacy & Numeracy up to date. | 20XX | Literacy Plan | Lit leaders committee meeting to approve plan | Draw up PD plan 2009 | LL & P | Provide copy of Plan for BOT & Staff | Carry out plan 2009 |
| 6. Other Curriculum Areas – review all programmes, pupil learning, new programmes | T2 T4 | Committee to plan year/now people review programmes Reports/Assessments | TOD 20 May TOD 23 Oct | Look at all curriculum plans, refine. Curriculum plans realigned. | Whole staff, Curriculum responsibility. Community consultation June 09 | Data gathered | Include when developing new reporting format |
| 7. Key Competencies |  | Professional Partnerships Advisor NZC Committee | Investigate & gather knowledge, SS. NZC 7th May Chch | Know possible ideas about how we will approach KCs. Findings shared on TOD | Ss SS NZC C | Notes to BOT Discussions about findings. |  |
| 8. ICT Development, Inquiry Learning, Thinking Skills |  | Forward planning for ICT – equipment - technician Have some staff training | ICT Committee to review where we are at – plan Provide PD | PD questionnaire BOT Equipment request Trained staff report back to other staff | ICT Committee P | Staff Meeting held. ICT minutes | BOT copy of minutes and recommendations March 09. |